## Project Cost NRS
Myagdi Khola HPP (65 MW)
PROJECT COST ESTIMATE
| Installed capacity (kW) |  | 65000
Item No. | Detail | % | Cost in NRs | VAT Complying % | VAT Complying Amount (NRs) | % Allocations
A | Civil Works
A.1 | Civil Surface Works |  | 1786698000 | 100% | 1786698000
A.2 | Civil Underground Works |  | 2455455000 | 100% | 2455455000
| Base Cost of Civil |  | 4242153000 |  |  | 36.48%
B | Electromechanical, Hydro-mechanical & Transmission Line
B.1 | Electro-mechanical Works including Accessories |  | 1794337000 | 5% | 89716850 |  | 1794337000 | 53830110 | 89716850
B.2 | Hydro-mechanical Works |  | 1011918000 | 50% | 505959000 |  | 17943370
B.3 | Transmission line including land acquition |  | 346500000 | 100% | 346500000 |  | 17943370 | 71773480 | 161490330
| Base Cost of EM,HM & TL |  | 3152755000 |  |  | 27.11%
| Total Base Cost (Total of A & B) |  | 7394908000
C | Infrastructures and Logistics
C.1 | Mobilization cost for initial infrastructural development |  | 80000000 | 100% | 80000000
C.2 | Access Road , Bridge Construction and Maintenance |  | 449505000 | 100% | 449505000
C.3 | Connecting Roads to Adits |  | 91250000 | 100% | 91250000
C.4 | Camp facilities |  | 150000000 | 100% | 150000000
C.5 | General Items (Bunker setup and running cost) |  | 35000000 | 100% | 35000000
| Total of Infrastructure Cost |  | 805755000 |  |  | 6.928%
D | EIA including mitigation and monitoring
| EIA Cost including mitigation and monitoring |  | 123461000 | 0% | 0
| Total EIA cost |  | 123461000 |  |  | 1.062%
E | Land Acquisition, Compensation and Development
| Land acquisition, Compensation and Development Cost (As per EIA) |  | 165000000 | 0% | 0
| Total Land cost |  | 165000000 |  |  | 1.419%
F | Engineering Design and Supervision Cost
F.1 | Design, Engineering and Supervision |  | 380000000 | 100% | 380000000
F.2 | Site Investigation costs |  | 50000000 | 100% | 50000000
F.3 | Physical Modelling costs |  | 30000000 | 100% | 30000000
| Total of Engineering Design and Supervision Cost |  | 460000000 |  |  | 3.955%
G | Project Management Cost during Construction
G.1 | Vehicle Setup, maintainance and running cost |  | 79000000 | 100% | 79000000
G.2 | Office equipment, computer, printer stationaries and running cost |  | 36000000 | 100% | 36000000
G.3 | Administrative and Management Cost |  | 100000000 | 100% | 100000000
| Total of Project Management Cost during Construction |  | 215000000 |  |  | 1.849%
H | Construction Power
| Construction Power to Project area and distribution works in the area |  | 100000000 | 100% | 100000000
| Total of Construction Power Cost |  | 100000000 |  |  | 0.8599%
I | Pre Project Development
| Pre Project Development Cost |  | 200000000 | 100% | 200000000
| Total of Pre project development cost |  | 200000000 |  |  | 1.72%
J | Insurance During Construction
| Insurance During Construction (1% of Total Base Cost) |  | 73949080 | 100% | 73949080
| Total of Insurance During Construction Cost |  | 73949080 |  |  | 0.6359%
K | Loan Management Cost
| Loan Management Cost (0.5% of Loan Amount) | 0.5% | 58148817.395
| Total of Loan Management Cost |  | 58148817.395
L | Contingencies
L.1 | Physical Contingencies
| Physical Contingency @ 10% for Surface Civil Works | 10% | 178669800 | 100% | 178669800
| Physical Contingency @ 15% for Underground Civil Works | 15% | 368318250 | 100% | 368318250
| Physical Contingency @ 4% for EM | 4% | 71773480 | 5% | 3588674
| Physical Contingency @ 5% for HM | 5% | 50595900 | 50% | 25297950
| Physical Contingency @ 5% for TL | 5% | 17325000 | 100% | 17325000
| Physical Contingency @ 5% for Infrastructure Works | 5% | 40287750 | 100% | 40287750
| Physical Contingency @ 5% for Construction Power | 5% | 5000000 | 100% | 5000000
| Total of Physical Contingencies |  | 731970180 |  |  | 6.294%
L.2 | Price Contingency
| Price Contingency @ 5 % of Civil base cost A | 5% | 212107650 | 100% | 212107650
| Price Contingency @ 3% of EM | 3% | 53830110 | 5% | 2691505.5
| Price Contingency @ 3% of HM | 3% | 30357540 | 50% | 15178770
| Price Contingency @ 3% of TL | 3% | 10395000 | 100% | 10395000
| Total of Price Contingencies |  | 306690300 |  |  | 2.637%
M | Custom Tax
| Custom duty applicable in none VAT complying amount | 1% | 23703793
| Total of Custom Tax |  | 23703793 |  |  | 0.2038%
N | VAT Amount
| Total VAT amount | 13% | 1029326126 |  |  | 8.851%
| Total TAX and VAT (Total of G and H) |  | 1053029919
| TOTAL PROJECT COST EXCLUDING VAT & TAX, NRs |  | 10576733560
| TOTAL PROJECT COST INCLUDING VAT & TAX, NRs |  | 11629763479
| TOTAL PROJECT COST INCLUDING VAT, NRs (in millions) |  | 11629.7635
| TOTAL PROJECT COST INCLUDING IDC, NRs |  | 12977428611.3267
| Unit cost (Without IDC) |  |  | 178919438.1385 | NRs./MW
| Unit cost (With IDC) |  |  | 199652747.8666 | NRs./MW
Financial Analysis assumptions
| IDC Calculated |  | 1289516314.9317
| Interest rate |  | 11%
| Construction Period |  | 3 | years
Disbursement
|  | 1st | 15%
|  | 2nd | 35%
|  | 3rd | 50%
Note on B26: Author: as per client
Note on B27: Author: as per client
Note on B37: Lenovo: rental, salary etc.

## Sheet1
8.4 | 103.11 | 115.26
4.8 | 232.88 | 263.67
| 866124000 | 968184000
| 1117824000 | 1265616000
| 1983948000 | 2233800000
Description | unit | As per PPA (57.3 MW) | Finalized Energy Table for PPA (65 MW)
Design Discharge | m3/s | 12.5 | 12.5
Gross Head | m | 564 | 629
Net Head | m | 537.62 | 600.76
Dry Energy | GWh | 103.11 | 115.26 | 11.78% | 12.15
Wet Energy | GWh | 232.88 | 263.67 | 13.22% | 30.79
Total Energy | GWh | 335.99 | 378.93 | 12.78% | 42.94
| Nrs. | 1983948000 | 2233800000
Annual Revenue Generation 1st year |  |  |  | 12.59%

## Project Cost NRS -57mW
Myagdi Khola HPP (65 MW)
PROJECT COST ESTIMATE
| Installed capacity (kW) |  | 57300
Item No. | Detail | % | Cost in NRs | VAT Complying % | VAT Complying Amount (NRs) | % Allocations
A | Civil Works
A.1 | Civil Surface Works |  | 1756698000 | 100% | 1756698000
A.2 | Civil Underground Works |  | 2455455000 | 100% | 2455455000
| Base Cost of Civil |  | 4212153000 |  |  | 37.09%
B | Electromechanical, Hydro-mechanical & Transmission Line
B.1 | Electro-mechanical Works including Accessories |  | 1581777078.4615 | 5% | 79088853.9231 |  | 1581777078.4615 | 47453312.3538 | 79088853.9231
B.2 | Hydro-mechanical Works |  | 1011918000 | 50% | 505959000 |  | 15817770.7846
B.3 | Transmission line including land acquition |  | 346500000 | 100% | 346500000 |  | 15817770.7846 | 63271083.1385 | 142359937.0615
| Base Cost of EM,HM & TL |  | 2940195078.4615 |  |  | 25.89%
| Total Base Cost (Total of A & B) |  | 7152348078.4615
C | Infrastructures and Logistics
C.1 | Mobilization cost for initial infrastructural development |  | 80000000 | 100% | 80000000
C.2 | Access Road , Bridge Construction and Maintenance |  | 449505000 | 100% | 449505000
C.3 | Connecting Roads to Adits |  | 91250000 | 100% | 91250000
C.4 | Camp facilities |  | 150000000 | 100% | 150000000
C.5 | General Items (Bunker setup and running cost) |  | 35000000 | 100% | 35000000
| Total of Infrastructure Cost |  | 805755000 |  |  | 7.095%
D | EIA including mitigation and monitoring
| EIA Cost including mitigation and monitoring |  | 123461000 | 0% | 0
| Total EIA cost |  | 123461000 |  |  | 1.087%
E | Land Acquisition, Compensation and Development
| Land acquisition, Compensation and Development Cost (As per EIA) |  | 165000000 | 0% | 0
| Total Land cost |  | 165000000 |  |  | 1.453%
F | Engineering Design and Supervision Cost
F.1 | Design, Engineering and Supervision |  | 380000000 | 100% | 380000000
F.2 | Site Investigation costs |  | 50000000 | 100% | 50000000
F.3 | Physical Modelling costs |  | 30000000 | 100% | 30000000
| Total of Engineering Design and Supervision Cost |  | 460000000 |  |  | 4.05%
G | Project Management Cost during Construction
G.1 | Vehicle Setup, maintainance and running cost |  | 79000000 | 100% | 79000000
G.2 | Office equipment, computer, printer stationaries and running cost |  | 36000000 | 100% | 36000000
G.3 | Administrative and Management Cost |  | 100000000 | 100% | 100000000
| Total of Project Management Cost during Construction |  | 215000000 |  |  | 1.893%
H | Construction Power
| Construction Power to Project area and distribution works in the area |  | 100000000 | 100% | 100000000
| Total of Construction Power Cost |  | 100000000 |  |  | 0.8805%
I | Pre Project Development
| Pre Project Development Cost |  | 200000000 | 100% | 200000000
| Total of Pre project development cost |  | 200000000 |  |  | 1.761%
J | Insurance During Construction
| Insurance During Construction (1% of Total Base Cost) |  | 71523481 | 100% | 71523481
| Total of Insurance During Construction Cost |  | 71523481 |  |  | 0.6298%
K | Loan Management Cost
| Loan Management Cost (0.5% of Loan Amount) | 0.5% | 56784797.0473
| Total of Loan Management Cost |  | 56784797.0473
L | Contingencies
L.1 | Physical Contingencies
| Physical Contingency @ 10% for Surface Civil Works | 10% | 175669800 | 100% | 175669800
| Physical Contingency @ 15% for Underground Civil Works | 15% | 368318250 | 100% | 368318250
| Physical Contingency @ 4% for EM | 4% | 63271083 | 5% | 3163554.15
| Physical Contingency @ 5% for HM | 5% | 50595900 | 50% | 25297950
| Physical Contingency @ 5% for TL | 5% | 17325000 | 100% | 17325000
| Physical Contingency @ 5% for Infrastructure Works | 5% | 40287750 | 100% | 40287750
| Physical Contingency @ 5% for Construction Power | 5% | 5000000 | 100% | 5000000
| Total of Physical Contingencies |  | 720467783 |  |  | 6.344%
L.2 | Price Contingency
| Price Contingency @ 5 % of Civil base cost A | 5% | 210607650 | 100% | 210607650
| Price Contingency @ 3% of EM | 3% | 47453312 | 5% | 2372665.6
| Price Contingency @ 3% of HM | 3% | 30357540 | 50% | 15178770
| Price Contingency @ 3% of TL | 3% | 10395000 | 100% | 10395000
| Total of Price Contingencies |  | 298813502 |  |  | 2.631%
M | Custom Tax
| Custom duty applicable in none VAT complying amount | 1% | 21543121
| Total of Custom Tax |  | 21543121 |  |  | 0.1897%
N | VAT Amount
| Total VAT amount | 13% | 1023047444 |  |  | 9.008%
| Total TAX and VAT (Total of G and H) |  | 1044590565
| TOTAL PROJECT COST EXCLUDING VAT & TAX, NRs |  | 10312368844.4615
| TOTAL PROJECT COST INCLUDING VAT & TAX, NRs |  | 11356959409.4615
| TOTAL PROJECT COST INCLUDING VAT, NRs (in millions) |  | 11356.9594
| TOTAL PROJECT COST INCLUDING IDC, NRs |  | 12673011815.2579
| Unit cost (Without IDC) |  |  | 198201734.8946 | NRs./MW
| Unit cost (With IDC) |  |  | 221169490.6677 | NRs./MW
Financial Analysis assumptions
| IDC Calculated |  | 1259267608.749
| Interest rate |  | 11%
| Construction Period |  | 3 | years
Disbursement
|  | 1st | 15%
|  | 2nd | 35%
|  | 3rd | 50%
Note on B26: Author: as per client
Note on B27: Author: as per client
Note on B37: Lenovo: rental, salary etc.